TRAKAGILE

CMMI Level 3-Aligned
Process Manual and Evidence Guide

Software Development and Maintenance | Controlled Working Draft

| Document ID | Version | Owner | Effective date |
| --- | --- | --- | --- |
| TA-QMS-001 | 1.0 | Quality / Engineering | 2026-08-18 |

Important: This manual is designed to support CMMI Maturity Level 3 readiness. It does not represent or imply a formal CMMI appraisal rating. Only an authorized appraisal can establish a maturity-level result.

Classification: Internal Controlled Document

# Document Control

| Role | Name / title | Responsibility | Approval |
| --- | --- | --- | --- |
| Process owner | Quality Manager | Maintain organizational standard processes | Pending |
| Business owner | Product Sponsor | Approve objectives and scope | Pending |
| Engineering owner | Engineering Manager | Approve lifecycle and technical controls | Pending |
| Project manager | TrakAgile PM | Tailor and implement this manual | Pending |

## Revision History

| Version | Date | Author | Change summary |
| --- | --- | --- | --- |
| 1.0 | 2026-08-18 | TrakAgile Team | Initial Level 3-aligned process baseline |

## Distribution and Retention

Controlled copy: Git repository documentation area or approved QMS repository.

Retention: project life plus three years, unless contractual or legal obligations require longer.

Changes require review by the process owner and affected functional owner.

# Contents

1. Purpose, scope and maturity intent

2. Organizational process architecture

3. Governance, roles and tailoring

4. Integrated project lifecycle

5. Requirements development and management

6. Project planning and monitoring

7. Risk and decision management

8. Configuration and change management

9. Process and product quality assurance

10. Verification, validation and release

11. Measurement and performance management

12. Training and organizational learning

13. Supplier and service management

14. Evidence and traceability matrix

15. Appraisal-readiness plan

Appendices: templates, records and glossary

# 1. Purpose, Scope and Maturity Intent

This manual defines the organizational standard processes used to plan, build, test, release and support the TrakAgile web and mobile applications. It establishes repeatable procedures, tailoring rules, objective evidence and governance expectations for software development and maintenance.

CMMI Maturity Level 3 is commonly described as Defined: organization-wide standards guide projects and work is managed proactively. Projects tailor approved organizational processes, use organizational assets and contribute lessons and measures back to the organization.

Scope: Next.js web application, backend route handlers, Flutter mobile application, Android packages, supporting data stores, deployment environments, and project-management activities performed by the TrakAgile delivery team.

## 1.1 Objectives

Deliver predictable scope, quality and release outcomes.

Maintain bidirectional traceability from business need to deployed release.

Detect risk and defects early through defined reviews and measurable quality gates.

Preserve configuration integrity across web, API and mobile baselines.

Create reusable organizational assets, measures and lessons for future projects.

## 1.2 Applicability and Exclusions

All TrakAgile changes follow this manual. Emergency fixes may use an expedited path but still require a recorded request, risk assessment, peer review, verification evidence and retrospective approval. No practice may be omitted solely to meet a schedule date.

# 2. Organizational Process Architecture

| Process layer | Purpose | Primary assets |
| --- | --- | --- |
| Policy | States mandatory governance expectations | Quality policy, security policy, release policy |
| Standard process | Defines the normal organizational workflow | This manual, lifecycle, role model, gates |
| Tailored project process | Adapts the standard process to project context | Project plan, tailoring record, sprint/release plan |
| Procedure / checklist | Provides repeatable operational steps | Review, testing, deployment, incident checklists |
| Record / evidence | Demonstrates performance and compliance | Tickets, commits, approvals, reports, test output, metrics |

## 2.1 Process Asset Library

The Quality Manager maintains a controlled Process Asset Library (PAL). Each asset has an identifier, owner, version, approval status, effective date and review date. Obsolete versions remain retrievable but are marked superseded.

| Asset class | Required examples | Repository location / record |
| --- | --- | --- |
| Plans | Project, quality, configuration, measurement, risk | docs/qms/plans/ |
| Standards | Coding, API, UI, mobile, security | docs/qms/standards/ |
| Templates | Requirement, review, test, release, retrospective | docs/qms/templates/ |
| Evidence | Approved records for each release | docs/qms/evidence/<release>/ |
| Measures | Definitions, raw data and baselines | docs/qms/metrics/ |

# 3. Governance, Roles and Tailoring

| Role | Accountability |
| --- | --- |
| Sponsor / Product Owner | Business objectives, priority, acceptance and release authorization |
| Project Manager | Integrated plan, commitments, status, dependencies, risks and stakeholder communication |
| Engineering Manager | Technical approach, capacity, standards, reviews and engineering quality |
| Developer | Design, implementation, unit evidence, peer-review response and traceability |
| QA Lead / Tester | Test strategy, independent verification, defect reporting and exit recommendation |
| Configuration Manager | Branches, baselines, release identification, integrity and recovery |
| Quality Manager | Process audits, nonconformance tracking, metrics and organizational learning |
| Security / Operations | Security review, deployment readiness, monitoring and incident response |

## 3.1 Tailoring Rules

- Classify the work as standard release, minor enhancement, defect fix or emergency change.

- Select lifecycle activities and evidence proportional to complexity, risk and customer impact.

- Record every deviation, rationale, risk, compensating control, approver and expiry date.

- Quality Manager reviews tailoring before execution; retrospective review is allowed only for emergencies.

- Feed approved improvements and reusable assets back into the PAL.

| Work class | Minimum evidence |
| --- | --- |
| Standard release | Approved scope, estimates, design, reviews, tests, risk log, release approval, retrospective |
| Minor enhancement | Requirement, impact assessment, peer review, focused tests, release note |
| Defect fix | Defect record, root cause, code review, regression evidence, closure approval |
| Emergency | Incident/change record, risk acceptance, review, focused verification, post-implementation review |

# 4. Integrated Project Lifecycle

| Stage | Entry criteria | Core activities | Exit evidence |
| --- | --- | --- | --- |
| Initiate | Approved business need | Scope, stakeholders, objectives, constraints | Charter and governance approval |
| Plan | Charter approved | Estimate, schedule, resources, risks, quality and measurement plans | Baselined integrated plan |
| Analyze / Design | Prioritized requirements | Elaboration, architecture, interface and data design | Reviewed requirement/design baseline |
| Build | Design ready | Implementation, unit tests, peer review, integration | Approved code and build artifacts |
| Verify / Validate | Testable build | Functional, regression, security and acceptance testing | Test summary and acceptance |
| Release | Exit criteria met | Approval, backup, deployment, smoke test, communications | Release record and baseline |
| Operate / Improve | Release live | Monitoring, incidents, feedback, metrics, retrospective | Lessons and improvement actions |

## 4.1 Stage-Gate Rule

A gate is passed only when required evidence is complete, exceptions are formally accepted and accountable owners approve progression. Gate decisions are recorded as Go, Conditional Go or No-Go.

# 5. Requirements Development and Management

## 5.1 Required Procedure

- Elicit needs from authorized stakeholders and identify operational scenarios for employee, manager, admin and director roles.

- Document functional, interface, data, security, performance, usability and regulatory requirements with acceptance criteria.

- Analyze conflicts, dependencies, feasibility and impact across web, backend and mobile clients.

- Obtain approval and establish a requirement baseline before implementation.

- Maintain status and bidirectional links among requirement, design, code, test, defect and release.

- Evaluate every change for scope, cost, schedule, risk, test and migration impact before approval.

## 5.2 Requirement Quality Checklist

Unique identifier and owner

Clear source and business rationale

Unambiguous and testable language

Acceptance criteria and priority

Dependencies and constraints

Security/privacy impact

Approved status and target release

| Trace element | Example TrakAgile evidence |
| --- | --- |
| Requirement | User story or approved change request for mobile attendance |
| Implementation | Commit and changed files under mobile/, app/api/mobile/ and attendance APIs |
| Verification | ESLint, Next.js build, Flutter analyzer/test logs, device test record |
| Release | Versioned APK record and release approval |

# 6. Project Planning and Monitoring

## 6.1 Integrated Plan Contents

Objectives and success measures

Scope and work breakdown

Estimation basis and assumptions

Milestones and dependencies

Resources, skills and environments

Quality and verification strategy

Risk and issue approach

Configuration and release strategy

Stakeholder communication

Data-management and retention needs

## 6.2 Monitoring Cadence

| Cadence | Review | Outputs |
| --- | --- | --- |
| Daily | Delivery blockers and environment health | Updated tasks and impediments |
| Weekly | Scope, schedule, quality, risk and dependency status | Status report and actions |
| Per pull request | Technical and security review | Approval and review evidence |
| Per release | Readiness and rollback review | Go/No-Go decision |
| Monthly | Process performance and improvement | Metrics analysis and improvement backlog |

Escalation: Variance beyond an approved threshold requires documented cause, impact, corrective action, owner and due date. Replanning is controlled; it does not erase the original baseline.

# 7. Risk and Decision Management

Risks are identified continuously and evaluated using Probability (1-5) x Impact (1-5). Scores 15-25 are High, 8-14 Medium and 1-7 Low. High risks require an owner, mitigation, contingency and management review.

| ID | Risk | P | I | Score | Response / evidence |
| --- | --- | --- | --- | --- | --- |
| R-01 | Mobile device cannot reach local API | 4 | 4 | 16 | Stable environment URL, network test, deployment endpoint |
| R-02 | Role authorization differs across web and mobile | 3 | 5 | 15 | Shared identity helper, role tests, access matrix |
| R-03 | Generated APK is confused with source baseline | 3 | 3 | 9 | Versioning, release storage, .gitignore rules |
| R-04 | Location permission or GPS failure | 3 | 4 | 12 | Permission handling, user message, device test |

## 7.1 Formal Decisions

Significant technical or process decisions use documented criteria, alternatives, assumptions, analysis, recommendation, approver and follow-up date. Examples include native Flutter versus responsive web, authentication strategy and release distribution method.

# 8. Configuration and Change Management

| Configuration item | Identification / control | Baseline evidence |
| --- | --- | --- |
| Web/backend source | Git repository, controlled branch and commit SHA | PreProd commit and approved merge |
| Mobile source | mobile/ directory and pubspec version | Tagged source commit |
| Dependencies | package-lock.json and pubspec.lock | Committed lock files |
| Configuration | Approved environment variable register; secrets excluded | Environment checklist |
| Release artifact | Versioned APK with checksum | Release repository entry |
| Process records | Document ID/version/approval | QMS repository baseline |

## 8.1 Change Flow

- Record request and rationale

- Analyze affected requirements, interfaces, security, data and tests

- Approve or reject through assigned authority

- Implement on controlled branch

- Peer-review and verify

- Baseline and release

- Confirm outcome and close

Generated binaries, screenshots, logs, local secrets and temporary files are not source-controlled. Release binaries are stored in an approved artifact repository with checksum, version, source commit and approval record.

# 9. Process and Product Quality Assurance

Quality assurance evaluates both process adherence and product work products. Reviewers are sufficiently independent of the activity being checked and report findings objectively.

| Review type | Sample | Criteria | Record |
| --- | --- | --- | --- |
| Process audit | Monthly or each major release | Required activities and evidence completed | Audit checklist/findings |
| Work-product review | Requirements, design, tests, release | Correct, complete, consistent, compliant | Review approval |
| Code review | Every change | Standards, security, maintainability, tests | PR/commit review |
| Release audit | Every production release | Baseline, approvals, rollback, communication | Release checklist |

## 9.1 Nonconformance Management

- Record the requirement or process not met and objective evidence.

- Classify severity and assign corrective-action owner and due date.

- Analyze root cause for major or recurring findings.

- Verify effectiveness before closure; escalate overdue items.

# 10. Verification, Validation and Release

| Test level | Purpose | Minimum evidence |
| --- | --- | --- |
| Static analysis | Detect code and style defects | ESLint / analyzer output |
| Unit | Verify isolated behavior | Automated test result |
| Integration / API | Verify contracts, authorization and data flow | API test report |
| System | Verify end-to-end business workflow | Scenario result and defects |
| Regression | Protect existing behavior | Regression suite summary |
| Device / compatibility | Verify Android permissions, network and UI | Device matrix and screenshots |
| User acceptance | Confirm business fitness | Authorized acceptance |

## 10.1 TrakAgile Release Quality Gate

Requirements and acceptance criteria approved

Code review complete

ESLint has zero errors and warnings

Next.js production build passes

Flutter analyzer and automated tests pass

Critical workflows pass on a representative Android device

Open defects accepted according to severity policy

Rollback and support readiness confirmed

Release version, checksum and source SHA recorded

Current evidence note: The repository contains successful Next.js lint/build evidence and a versioned mobile build. Formal Level 3 readiness also requires retained, repeatable records for each release and device-based validation evidence.

# 11. Measurement and Performance Management

| Measure | Definition | Frequency | Owner | Use |
| --- | --- | --- | --- | --- |
| Schedule variance | Actual milestone date minus baseline | Weekly | PM | Forecast and corrective action |
| Scope stability | Approved changes / baselined requirements | Release | PO/PM | Plan and requirement quality |
| Defect escape rate | Post-release defects / total defects | Release | QA | Test effectiveness |
| Build success rate | Successful CI builds / total builds | Weekly | Engineering | Integration health |
| Review effectiveness | Defects found before test / total defects | Release | Engineering/QA | Peer-review quality |
| Mean resolution time | Average time from defect open to verified close | Monthly | QA | Flow improvement |
| Process compliance | Conforming checks / applicable checks | Monthly | Quality | Institutionalization |

## 11.1 Measurement Rules

Each measure has an operational definition, source, collection method, responsible owner, validation rule, reporting cadence and decision threshold. Raw data is retained with reports. Measures are analyzed for trends and used to make decisions, not merely collected.

# 12. Training and Organizational Learning

| Role | Required capability |
| --- | --- |
| All team members | Lifecycle, quality policy, security awareness, configuration discipline |
| Product / BA | Elicitation, acceptance criteria, traceability and change control |
| Developers | Next.js/Flutter standards, secure coding, review and testing |
| QA | Risk-based testing, evidence, defect lifecycle and independence |
| PM / Leads | Estimation, monitoring, risk, decisions, metrics and tailoring |
| Quality | Audit, causal analysis, corrective action and appraisal evidence |

Training records include need, course or mentoring activity, attendee, completion date and effectiveness evaluation. Retrospectives and root-cause analyses produce candidate process improvements; approved changes update organizational assets and are communicated before use.

# 13. Supplier and Service Management

Externally supplied software, cloud services, libraries, signing services and hosting providers are selected and monitored according to risk. Agreements define scope, acceptance, security, service levels, support, data handling and exit obligations.

Maintain approved supplier and dependency inventory

Evaluate license, vulnerability, support and compatibility risk

Verify delivered products/services against acceptance criteria

Monitor performance and resolve variances

Plan replacement or recovery for critical suppliers

# 14. Evidence and Traceability Matrix

| Process objective | Expected objective evidence | TrakAgile status |
| --- | --- | --- |
| Defined lifecycle | Approved standard process and tailored project plan | Manual created; project tailoring approval required |
| Managed requirements | Baselines, change records, trace links | Implement traceability register |
| Planned and monitored work | Plan, estimates, status, corrective actions | Retain periodic status records |
| Risk management | Risk register, reviews, mitigations | Initial risks provided; maintain live register |
| Configuration integrity | Repository, branches, baselines, release records | Git/PreProd established; formal release register needed |
| Quality assurance | Audit plan, checklists, findings and closures | Establish independent audit cadence |
| Verification and validation | Test plans/results, defects, acceptance | Build checks exist; retain API/device/UAT evidence |
| Measurement | Definitions, repository, analysis and actions | Establish baseline dashboard |
| Training | Skills matrix, plan, records, effectiveness | Create team skills/training register |
| Organizational learning | Lessons, causal analysis, updated assets | Create PAL improvement workflow |

# 15. Appraisal-Readiness Plan

| Phase | Target outcome | Key actions |
| --- | --- | --- |
| 1. Baseline | Approved organizational process set | Approve this manual, owners, templates and tailoring rules |
| 2. Deploy | Processes used consistently | Train team; execute on at least two representative releases |
| 3. Measure | Objective performance evidence | Collect measures, analyze trends, document decisions |
| 4. Audit | Gaps known and corrected | Internal audits, evidence sampling, corrective actions |
| 5. Prepare | Appraisal evidence organized | Map artifacts, interview roles, resolve gaps |
| 6. Appraise | Independent determination | Engage an authorized CMMI appraisal professional |

## 15.1 Readiness Exit Criteria

Organizational processes and tailoring are approved and in use

Representative projects demonstrate consistent performance

Required evidence is complete, attributable and retrievable

Measures show management use and improvement

Audit findings are closed or formally managed

Staff can explain their roles and actual process use

# Appendix A - Required Templates and Records

| ID | Template / record | Minimum fields |
| --- | --- | --- |
| TA-TPL-001 | Project Plan | Scope, estimates, milestones, resources, dependencies, approvals |
| TA-TPL-002 | Tailoring Record | Selected process, deviation, rationale, risk, approver |
| TA-TPL-003 | Requirements & Traceability Register | ID, source, criteria, code, test, release, status |
| TA-TPL-004 | Risk / Issue Register | Cause, event, effect, rating, owner, response, status |
| TA-TPL-005 | Decision Record | Context, options, criteria, analysis, decision, approver |
| TA-TPL-006 | Peer Review Checklist | Change, reviewers, criteria, findings, resolution |
| TA-TPL-007 | Test Plan and Summary | Scope, environment, cases, results, defects, recommendation |
| TA-TPL-008 | Release Checklist | Version, SHA, gates, rollback, approvals, verification |
| TA-TPL-009 | Process Audit | Sample, criteria, evidence, finding, action, closure |
| TA-TPL-010 | Measurement Definition | Purpose, formula, source, owner, frequency, threshold |
| TA-TPL-011 | Retrospective / Lessons | Outcome, causes, learning, action, PAL candidate |
| TA-TPL-012 | Training Record | Need, participant, activity, completion, effectiveness |

# Appendix B - Sample Release Record

| Field | Required value |
| --- | --- |
| Release ID | TrakAgile <version/build> |
| Scope | Approved requirement/change identifiers |
| Source baseline | Git branch, tag and full commit SHA |
| Build artifact | APK/package name and SHA-256 checksum |
| Verification | Lint, build, automated, API, device and UAT results |
| Known issues | Defect IDs, severity, business acceptance |
| Deployment | Environment, date/time, executor and outcome |
| Rollback | Procedure and trigger |
| Approvals | Product, Engineering, QA, Operations |
| Post-release | Smoke test, monitoring and retrospective links |

# Appendix C - Glossary

| Term | Definition |
| --- | --- |
| Baseline | A formally reviewed and agreed configuration used as the basis for further work. |
| CMMI | Capability Maturity Model Integration, a performance and process-improvement framework. |
| Defined process | A managed process tailored from approved organizational standards. |
| Objective evidence | Verifiable information demonstrating that an activity occurred or a result exists. |
| PAL | Process Asset Library containing controlled standards, templates, measures and lessons. |
| Tailoring | Approved adaptation of an organizational standard process for project characteristics. |
| Traceability | Links connecting needs, requirements, implementation, verification and release. |

# References

CMMI Institute, “CMMI Levels of Capability and Performance,” official maturity-level overview: https://cmmiinstitute.com/learning/appraisals/levels

CMMI Institute, “Appraisals,” official overview of appraisals and benchmark maturity/capability achievement: https://cmmiinstitute.com/learning/appraisals

CMMI Institute, “CMMI Model Quick Reference Guide,” official condensed model orientation: https://cmmiinstitute.com/Resource-Files/Public/CMMI-Model-Quick-Reference-Guide

Internal evidence baseline: TrakAgile repository, PreProd branch, commit 0303bcf and subsequent approved changes.